## Overview
Floor test matrix: bare against enclosed
Share of planned trials done for each floor, condition, day and radius. Fill in the yellow Done column on the Trials sheet; this grid updates itself.
Drops per radius per block |  | 5 | 5 per the procedure (section 1); 3 when short on time.
Floor | Condition | Day 1 |  |  |  | Day 2 |  |  |  | All
|  | 1 m | 2 m | 3 m | Noise baselines | 1 m | 2 m | 3 m | Noise baselines
tile | Bare | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Enclosed | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
wood | Bare | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Enclosed | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
carpet | Bare | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Enclosed | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
All floors |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Every planned trial done
Started, not finished
Not started
Each grid cell covers both blocks of that condition (blocks 1 and 3 bare, 2 and 4 enclosed), so 100% at a radius is 2 × the drops per block.
Noise baselines: one 60 s baseline per block, so 2 per condition per day.
Day 2 repeats the same plan on the same floor on a different day and at a different time of day.
The procedure is docs/testing/floor_procedure.md.

## Trials
Floor | Day | Block | Condition | ID prefix | Radius | Planned | Done | Status | Date done | Notes | Counted (auto)
tile | Day 1 | 1 | Bare | tile_bare_1 | Noise baseline | 1 |  | Not started |  |  | 0
tile | Day 1 | 1 | Bare | tile_bare_1 | 1 m | 5 |  | Not started |  |  | 0
tile | Day 1 | 1 | Bare | tile_bare_1 | 2 m | 5 |  | Not started |  |  | 0
tile | Day 1 | 1 | Bare | tile_bare_1 | 3 m | 5 |  | Not started |  |  | 0
tile | Day 1 | 2 | Enclosed | tile_vase_1 | Noise baseline | 1 |  | Not started |  |  | 0
tile | Day 1 | 2 | Enclosed | tile_vase_1 | 1 m | 5 |  | Not started |  |  | 0
tile | Day 1 | 2 | Enclosed | tile_vase_1 | 2 m | 5 |  | Not started |  |  | 0
tile | Day 1 | 2 | Enclosed | tile_vase_1 | 3 m | 5 |  | Not started |  |  | 0
tile | Day 1 | 3 | Bare | tile_bare_2 | Noise baseline | 1 |  | Not started |  |  | 0
tile | Day 1 | 3 | Bare | tile_bare_2 | 1 m | 5 |  | Not started |  |  | 0
tile | Day 1 | 3 | Bare | tile_bare_2 | 2 m | 5 |  | Not started |  |  | 0
tile | Day 1 | 3 | Bare | tile_bare_2 | 3 m | 5 |  | Not started |  |  | 0
tile | Day 1 | 4 | Enclosed | tile_vase_2 | Noise baseline | 1 |  | Not started |  |  | 0
tile | Day 1 | 4 | Enclosed | tile_vase_2 | 1 m | 5 |  | Not started |  |  | 0
tile | Day 1 | 4 | Enclosed | tile_vase_2 | 2 m | 5 |  | Not started |  |  | 0
tile | Day 1 | 4 | Enclosed | tile_vase_2 | 3 m | 5 |  | Not started |  |  | 0
tile | Day 2 | 1 | Bare | tile_bare_1 | Noise baseline | 1 |  | Not started |  |  | 0
tile | Day 2 | 1 | Bare | tile_bare_1 | 1 m | 5 |  | Not started |  |  | 0
tile | Day 2 | 1 | Bare | tile_bare_1 | 2 m | 5 |  | Not started |  |  | 0
tile | Day 2 | 1 | Bare | tile_bare_1 | 3 m | 5 |  | Not started |  |  | 0
tile | Day 2 | 2 | Enclosed | tile_vase_1 | Noise baseline | 1 |  | Not started |  |  | 0
tile | Day 2 | 2 | Enclosed | tile_vase_1 | 1 m | 5 |  | Not started |  |  | 0
tile | Day 2 | 2 | Enclosed | tile_vase_1 | 2 m | 5 |  | Not started |  |  | 0
tile | Day 2 | 2 | Enclosed | tile_vase_1 | 3 m | 5 |  | Not started |  |  | 0
tile | Day 2 | 3 | Bare | tile_bare_2 | Noise baseline | 1 |  | Not started |  |  | 0
tile | Day 2 | 3 | Bare | tile_bare_2 | 1 m | 5 |  | Not started |  |  | 0
tile | Day 2 | 3 | Bare | tile_bare_2 | 2 m | 5 |  | Not started |  |  | 0
tile | Day 2 | 3 | Bare | tile_bare_2 | 3 m | 5 |  | Not started |  |  | 0
tile | Day 2 | 4 | Enclosed | tile_vase_2 | Noise baseline | 1 |  | Not started |  |  | 0
tile | Day 2 | 4 | Enclosed | tile_vase_2 | 1 m | 5 |  | Not started |  |  | 0
tile | Day 2 | 4 | Enclosed | tile_vase_2 | 2 m | 5 |  | Not started |  |  | 0
tile | Day 2 | 4 | Enclosed | tile_vase_2 | 3 m | 5 |  | Not started |  |  | 0
wood | Day 1 | 1 | Bare | wood_bare_1 | Noise baseline | 1 |  | Not started |  |  | 0
wood | Day 1 | 1 | Bare | wood_bare_1 | 1 m | 5 |  | Not started |  |  | 0
wood | Day 1 | 1 | Bare | wood_bare_1 | 2 m | 5 |  | Not started |  |  | 0
wood | Day 1 | 1 | Bare | wood_bare_1 | 3 m | 5 |  | Not started |  |  | 0
wood | Day 1 | 2 | Enclosed | wood_vase_1 | Noise baseline | 1 |  | Not started |  |  | 0
wood | Day 1 | 2 | Enclosed | wood_vase_1 | 1 m | 5 |  | Not started |  |  | 0
wood | Day 1 | 2 | Enclosed | wood_vase_1 | 2 m | 5 |  | Not started |  |  | 0
wood | Day 1 | 2 | Enclosed | wood_vase_1 | 3 m | 5 |  | Not started |  |  | 0
wood | Day 1 | 3 | Bare | wood_bare_2 | Noise baseline | 1 |  | Not started |  |  | 0
wood | Day 1 | 3 | Bare | wood_bare_2 | 1 m | 5 |  | Not started |  |  | 0
wood | Day 1 | 3 | Bare | wood_bare_2 | 2 m | 5 |  | Not started |  |  | 0
wood | Day 1 | 3 | Bare | wood_bare_2 | 3 m | 5 |  | Not started |  |  | 0
wood | Day 1 | 4 | Enclosed | wood_vase_2 | Noise baseline | 1 |  | Not started |  |  | 0
wood | Day 1 | 4 | Enclosed | wood_vase_2 | 1 m | 5 |  | Not started |  |  | 0
wood | Day 1 | 4 | Enclosed | wood_vase_2 | 2 m | 5 |  | Not started |  |  | 0
wood | Day 1 | 4 | Enclosed | wood_vase_2 | 3 m | 5 |  | Not started |  |  | 0
wood | Day 2 | 1 | Bare | wood_bare_1 | Noise baseline | 1 |  | Not started |  |  | 0
wood | Day 2 | 1 | Bare | wood_bare_1 | 1 m | 5 |  | Not started |  |  | 0
wood | Day 2 | 1 | Bare | wood_bare_1 | 2 m | 5 |  | Not started |  |  | 0
wood | Day 2 | 1 | Bare | wood_bare_1 | 3 m | 5 |  | Not started |  |  | 0
wood | Day 2 | 2 | Enclosed | wood_vase_1 | Noise baseline | 1 |  | Not started |  |  | 0
wood | Day 2 | 2 | Enclosed | wood_vase_1 | 1 m | 5 |  | Not started |  |  | 0
wood | Day 2 | 2 | Enclosed | wood_vase_1 | 2 m | 5 |  | Not started |  |  | 0
wood | Day 2 | 2 | Enclosed | wood_vase_1 | 3 m | 5 |  | Not started |  |  | 0
wood | Day 2 | 3 | Bare | wood_bare_2 | Noise baseline | 1 |  | Not started |  |  | 0
wood | Day 2 | 3 | Bare | wood_bare_2 | 1 m | 5 |  | Not started |  |  | 0
wood | Day 2 | 3 | Bare | wood_bare_2 | 2 m | 5 |  | Not started |  |  | 0
wood | Day 2 | 3 | Bare | wood_bare_2 | 3 m | 5 |  | Not started |  |  | 0
wood | Day 2 | 4 | Enclosed | wood_vase_2 | Noise baseline | 1 |  | Not started |  |  | 0
wood | Day 2 | 4 | Enclosed | wood_vase_2 | 1 m | 5 |  | Not started |  |  | 0
wood | Day 2 | 4 | Enclosed | wood_vase_2 | 2 m | 5 |  | Not started |  |  | 0
wood | Day 2 | 4 | Enclosed | wood_vase_2 | 3 m | 5 |  | Not started |  |  | 0
carpet | Day 1 | 1 | Bare | carpet_bare_1 | Noise baseline | 1 |  | Not started |  |  | 0
carpet | Day 1 | 1 | Bare | carpet_bare_1 | 1 m | 5 |  | Not started |  |  | 0
carpet | Day 1 | 1 | Bare | carpet_bare_1 | 2 m | 5 |  | Not started |  |  | 0
carpet | Day 1 | 1 | Bare | carpet_bare_1 | 3 m | 5 |  | Not started |  |  | 0
carpet | Day 1 | 2 | Enclosed | carpet_vase_1 | Noise baseline | 1 |  | Not started |  |  | 0
carpet | Day 1 | 2 | Enclosed | carpet_vase_1 | 1 m | 5 |  | Not started |  |  | 0
carpet | Day 1 | 2 | Enclosed | carpet_vase_1 | 2 m | 5 |  | Not started |  |  | 0
carpet | Day 1 | 2 | Enclosed | carpet_vase_1 | 3 m | 5 |  | Not started |  |  | 0
carpet | Day 1 | 3 | Bare | carpet_bare_2 | Noise baseline | 1 |  | Not started |  |  | 0
carpet | Day 1 | 3 | Bare | carpet_bare_2 | 1 m | 5 |  | Not started |  |  | 0
carpet | Day 1 | 3 | Bare | carpet_bare_2 | 2 m | 5 |  | Not started |  |  | 0
carpet | Day 1 | 3 | Bare | carpet_bare_2 | 3 m | 5 |  | Not started |  |  | 0
carpet | Day 1 | 4 | Enclosed | carpet_vase_2 | Noise baseline | 1 |  | Not started |  |  | 0
carpet | Day 1 | 4 | Enclosed | carpet_vase_2 | 1 m | 5 |  | Not started |  |  | 0
carpet | Day 1 | 4 | Enclosed | carpet_vase_2 | 2 m | 5 |  | Not started |  |  | 0
carpet | Day 1 | 4 | Enclosed | carpet_vase_2 | 3 m | 5 |  | Not started |  |  | 0
carpet | Day 2 | 1 | Bare | carpet_bare_1 | Noise baseline | 1 |  | Not started |  |  | 0
carpet | Day 2 | 1 | Bare | carpet_bare_1 | 1 m | 5 |  | Not started |  |  | 0
carpet | Day 2 | 1 | Bare | carpet_bare_1 | 2 m | 5 |  | Not started |  |  | 0
carpet | Day 2 | 1 | Bare | carpet_bare_1 | 3 m | 5 |  | Not started |  |  | 0
carpet | Day 2 | 2 | Enclosed | carpet_vase_1 | Noise baseline | 1 |  | Not started |  |  | 0
carpet | Day 2 | 2 | Enclosed | carpet_vase_1 | 1 m | 5 |  | Not started |  |  | 0
carpet | Day 2 | 2 | Enclosed | carpet_vase_1 | 2 m | 5 |  | Not started |  |  | 0
carpet | Day 2 | 2 | Enclosed | carpet_vase_1 | 3 m | 5 |  | Not started |  |  | 0
carpet | Day 2 | 3 | Bare | carpet_bare_2 | Noise baseline | 1 |  | Not started |  |  | 0
carpet | Day 2 | 3 | Bare | carpet_bare_2 | 1 m | 5 |  | Not started |  |  | 0
carpet | Day 2 | 3 | Bare | carpet_bare_2 | 2 m | 5 |  | Not started |  |  | 0
carpet | Day 2 | 3 | Bare | carpet_bare_2 | 3 m | 5 |  | Not started |  |  | 0
carpet | Day 2 | 4 | Enclosed | carpet_vase_2 | Noise baseline | 1 |  | Not started |  |  | 0
carpet | Day 2 | 4 | Enclosed | carpet_vase_2 | 1 m | 5 |  | Not started |  |  | 0
carpet | Day 2 | 4 | Enclosed | carpet_vase_2 | 2 m | 5 |  | Not started |  |  | 0
carpet | Day 2 | 4 | Enclosed | carpet_vase_2 | 3 m | 5 |  | Not started |  |  | 0
Note on H1: Number of good trials recorded (invalid trials that were repeated count once). For noise baseline rows, 1 when the 60 s baseline is recorded.
Note on L1: Done, capped at Planned. Feeds the Overview grid. Do not edit.

## How to use
How to use this matrix
Edit only the yellow cells.
Trials sheet: Done (number of good trials), Date done, Notes.
Overview sheet: Drops per radius per block (C4), if you run 3 drops instead of 5.
Everything else is a label or a formula.
One row per block and radius. Each block starts with its noise baseline row, then 1, 2 and 3 m.
Shuffle the radius order inside each block when you run it (procedure section 1); the row order here is only for the checklist.
A trial marked invalid and repeated counts once. Write the reason in Notes.
Filter the Trials sheet by Floor, Day or Status to see what is left.
Example of a filled-in row (not counted anywhere):
Floor | Day | Block | Condition | ID prefix | Radius | Planned | Done | Status | Date done | Notes
tile | Day 1 | 2 | Enclosed | tile_vase_1 | 2 m | 5 | 4 | Partial | 2026-10-22 | drop 3 repeated (ball rolled); one left to do